## Sheet1
Name | Duration | Start | End | Pre | Name of the person
Mandate definition and planning | 4days | 2020-02-07 08:00 | 2020-02-07 17:00
Data collection | 0.25day | 2020-02-07 08:00 | 2020-02-07 03:00 | 4 | Gurpreet Jhamat
Research | 0.25day | 2020-02-08 09:00 | 2020-02-08 13:00 | 3 | Gurpreet Jhamat
Theoretical Solution | 0.5day | 2020-02-08 14:00 | 2020-02-08 21:00 | 8 | Gurveer Sandhu
Architecture Design | 0.5day | 2020-02-09 08:00 | 2020-02-09 16:00 | 8 | Gurveer Sandhu
Production script | 0.25day | 2020-02-09 16:00 | 2020-02-09 20:00 | 3 | Gurpreet Jhamat
Production planning | 0.25day | 2020-02-09 20:00 | 2020-02-09 | 2 | Gurveer Sandhu
Chient presentation + approval | 2day | 2020-02-10 09:00 | 2020-02-11 20:00 | 1 | Gurpreet Jhamat
Visual Design | 6days | 2020-02-12 10:00 | 2020-02-18 16:00
Research | 1day | 2020-02-12 10:00 | 2020-02-12 17:00 | 6 | Gurveer Sandhu
Ideation | 1day | 2020-02-13 09:00 | 2020-02-13 18:00 | 6 | Gurveer Sandhu
Conceptulization | 2day | 2020-02-14 11:00 | 2020-02-15 16:00 | 12 | Gurveer Sandhu
Mock-ups | 2days | 2020-02-16 09:00 | 2020-02-17 17:00 | 12 | Gurpreet Jhamat
Client presentation + approval | 1days | 2020-02-17 11:00 | 2020-02-18 16:00 | 14 | Gurpreet Jhamat
AIpha version | 4days | 2020-02-18 11:00 | 2020-02-19 16:00
Interface segmentation | .25days | 2020-02-19 11:00 | 2020-02-20 16:00 | 3 | Gurpreet Jhamat
Interfate Integration (desktop) | 0.25days | 2020-02-20 11:00 | 2020-02-21 16:00 | 3 | Gurveer Sandhu
Interface Integration (responsive: tablet / adaptive: mobile) | 0.75days | 2020-02-21 11:00 | 2020-02-22 16:00 | 4 | Gurveer Sandhu
Navigation Integration (responsive + adaptive) | 0.25days | 2020-02-22 11:00 | 2020-02-23 16:00 | 6 | Gurveer Sandhu
Alpha pages production (responsive + adaptive) | 0.25days | 2020-02-23 11:00 | 2020-02-24 16:00 | 4 | Gurpreet Jhamat
Home page production (responsive + adaptive) | 1days | 2020-02-24 11:00 | 2020-02-25 16:00 | 2 | Gurpreet Jhamat
Testing and corrections | 0.50days | 2020-02-25 11:00 | 2020-02-26 16:00 |  | Gurveer Sandhu
Client presentation + approval | 1days | 2020-02-26 11:00 | 2020-02-27 16:00 | 5 | Gurpreet Jhamat
Beta version | 3days | 2020-02-27 11:00 | 2020-02-28 16:00
Image creation/formatting | 0.25days | 2020-02-28 11:00 | 2020-02-29 16:00 | 3 | Gurpreet Jhamat
Titles + headings Integration | 0.25days | 2020-02-29 11:00 | 2020-03-01 16:00 | 3 | Gurpreet Jhamat
Texts and images Integration | 0.25days | 2020-03-01 11:00 | 2020-03-02 16:00 | 4 | Gurveer Sandhu
Programming: home page user local weather background selector | 0.25days | 2020-03-02 11:00 | 2020-03-03 16:00 | 6 | Gurpreet Jhamat
Programming: site search-engine | 0.25days | 2020-03-03 11:00 | 2020-03-04 16:00 | 7 | Gurveer Sandhu
Programs Integration | 0.25days | 2020-03-04 11:00 | 2020-03-05 16:00 | 4 | Gurveer Sandhu
Testing and corrections | 0.25days | 2020-03-05 11:00 | 2020-03-06 16:00 | 4 | Gurpreet Jhamat
Client presentation + approval | 1days | 2020-03-06 11:00 | 2020-03-07 16:00 | 2 | Gurveer Sandhu
lmplantatlon / deployment | 5days | 2020-03-07 11:00 | 2020-03-08 16:00
FInaliIe SEO | 1days | 2020-03-08 11:00 | 2020-03-09 16:00 | 3 | Gurveer Sandhu
Final corrections and adjustments | 1days | 2020-03-09 11:00 | 2020-03-10 16:00 | 3 | Gurveer Sandhu
FTP trans'er | 1days | 2020-03-10 11:00 | 2020-03-11 16:00 | 4 | Gurpreet Jhamat
Onllne tests | 1days | 2020-03-11 11:00 | 2020-03-12 16:00 | 2 | Gurpreet Jhamat
Corrections/adjustments | 1days | 2020-03-12 11:00 | 2020-03-13 16:00 | 8 | Gurpreet Jhamat